### Livonian songs from Loorits, notes

12.2.2026

harmonisoidaanko laulajatiedot? (tyttönimi - miehen nimi) Ei tässä kohtaa

paikkatieto Liivinrannalle

mitä tehdään lajijaottelun kanssa = miten merkitään (saksankielisiä ylä- ja alalajiotsikoita suoraan kirjasta)

y-kenttään vain yksi vuosiluku (ensimmäinen, jos kaksi vaihtoehtoista)

****

metadata 200a/8: tästä etenpäin läpilukematonta transkriptiota ja puuttuvia metatietoja

README

to get the songs in Volkslieder der Liven (Oskar Loorits 1936) into a proper text corpus with structured metadata, possibly also text versions in contemporary Livonian orthography.

- The book is available in two digital versions (freely available version here).

  - Both have very lousy automatic OCR done.

  - Sakari did quickly put one of these versions into xml code.

  - In closer inspection: lots of character level problems, diacritics mostly wrong, translations into Latvian mixed with original texts.

- Probably quicker to redo with Transkribus than to correct the old version

  - probably no ready-made models for Livonian (especially in old orthography)

  - would some Latvian model work for the orthography?

  - Mirjami corrects 4 pages by hand (taking time of how long a page takes)

    - for now, it is ok to mark diacritics as one character (most diacritics probably need to be changed into character + code combinations, can be done later)

  - Mirjami and Jakob test to make a Transcribus model

    - also need to use some model for German and Latvian

  - Mirjami goes through the book with Transcribus and makes a structured text file

    - first the relevant parts of the book, then to add the songs with metadata fields?

    - to include the translations as separate parts after each song

- to add the metadata from the end (and elsewhere) of the book

- to put the metadata and songs into xml (half-automatically by Jakob?)

- the data to Maciej to add to the FILTER database (Mirjami and Jakob would like to follow and see how this is done)

Metadata fields as separate rows before the song text, to mark with “–” if no information (?)

- place (LOC):  home place of the singer / place of recording if the singer not known

- collector (COL): (not Loorits, but the recorder of the actual song

- year (TMP) of recording

- signum (SGN): archival signum or such – do we need/already have a field for the number of the song in the book?

- name of the singer, if known

- any contextual information about the song, singer, context or such (INF)

XML code

- Sakari’s file is mostly fine

- p (place) and k (kerääjä) attributes need to be listed and added to the place and collector tables

- a new field is needed for the publication place and publisher (also for the whole KR (literary poems) collection): LOC field should be the “home/recording place of the song version”, COL is the recorder of the song (sometimes same as the publisher though)

- if the names of the singers are known for some songs, better to add a separate metadata field for these (to separate these from more heterogenous INF)

Questions:

how to mark the Latvian parallel texts in the code?

how to mark the German translations?

miten merkitään säkeen sisään/marginaaliin merkityt säevariaatiot

For Kati to ask from the Livonian Institute & Miina Norvik, maybe also Niko Partanen

- any Transkribus models for Livonian?

- Valts Ernštreits: to have a meeting after the Midsummer in Riga to check what would be useful for the Livonian Institute

Latviannokset vain jos informantti on osannut (eivät käännöksiä vaan versioita)

Decisions about working with the text

- Texts with a space between each character are going to be changed to italics. <i>Italics Text</i>

- to do also prose texts, also German ones, but to do long sequences last

- >-merkit ei toimi: vaihdettu nuoliksi (teksti otettu lähteestä xx)

To do

- check the tag names (in relation to SKVR & JR & standards)

- metakommentteihin esim. rinnakain asetellut liivi-latvia, joissa refrenki vain liivinkielisessä, mutta selvästi tarkoittaa myös latviankieliseen (ehkä)

- päiväysten merkintä etenkin, jos päivämäärä puuttuu, kuukausi on

- MITEN MERKITÄÄN KIELIVARIANTIT?

Metatekstiin

- variantit jaettu omiksi teksteikseen

- joskus variantissa vain viite toiseen laulutyyppiin (kahden laulutyypin väliin sijoittuvat laulut), nämä pidetty mukana

Toistaiseksi

kursiivilla latviankielisiä versioita

tyhjällä rivillä säkeistöjen välit, jos merkattu typografisesti kirjaan

joitain runoja on rivitetty säkeittäin, jos ovat olleet pidempinä lausekkeina, tämä kesken